## Gantt Chart
Task | Start | End | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-07 | 2027-06-14 | 2027-06-21 | 2027-06-28 | 2027-07-05 | 2027-07-12 | 2027-07-19 | 2027-07-26 | 2027-08-02 | 2027-08-09 | 2027-08-16 | 2027-08-23
Preparatory Meetings
Establishing the project teams | 2025-09-01 | 2025-09-07
The Online start up | 2025-09-08 | 2025-09-14
Staff Meetings at organisations | 2025-09-15 | 2025-09-21
Administrative Meeting in Portugal | 2025-11-11 | 2025-11-14
Create a GOOGLE DRIVE folder | 2025-11-10 | 2025-11-16
Reguler Online Meetings | 2025-12-15 | 2027-05-31
Quarterly Progress Reports | 2026-02-09 | 2027-05-10
WP 2 Workshops
Creating a project website/YouTube channel | 2026-02-23 | 2026-02-28
Poland-Basic Level Composition Training | 2026-03-02 | 2026-03-05
Turkiye-Digital recording training and joint product preparation | 2026-06-01 | 2026-06-04
Preparing a digital competence e-guide | 2026-06-22 | 2026-06-26
Preparing a social cohesion e-guide | 2026-06-29 | 2026-07-03
Preparing a DM-based lesson plan | 2026-11-02 | 2026-11-15
Romania-Cultural interaction workshop - Psychosocial support presentation for migrants | 2026-11-16 | 2026-11-19
Establishing DM recording studios in schools | 2026-12-01 | 2026-12-31
Online concert | 2027-02-25 | 2027-02-25
Final Competition | 2027-03-01 | 2027-05-01
Wp 3
Social media sharing-local activity | 2025-11-15 | 2027-06-10
providing open-access educational materials-local activity | 2026-04-01 | 2026-12-15
etwinning project application-local activity | 2026-11-16 | 2026-11-16
sharing knowledge, experience | 2027-01-01 | 2027-04-01
Partner institutions sharing project results within their own schools and networks | 2027-05-01 | 2027-05-30
Final Conference | 2027-06-07 | 2027-06-07
Establishing sustainable partnerships | 2027-06-15 | 2027-06-30
Creating a collaborative digital community for communication | 2027-06-20 | 2027-06-20

## Help
Project Start Date | 2025-09-01
Days Per Column | 7
Instructions
1. Update "Project Start Date" and "Days Per Column" above.
2. Update the gantt chart rows with task names, start dates, and end dates.
3. The template will automatically fill the gantt chart bars.
Provided By
onlinegantt.com - Free Online Gantt Chart Software